OUTLINE PROJECT PLAN FOR THE FALMOUTH NEIGHBOURHOOD PLAN/A4D PROCESS

| Phases | Stages | Actions | Timetable (Note Months are inclusive) |
| --- | --- | --- | --- |
| Laying the foundations | Stage 1: Starting up | Getting started: Town Council Authority Defining the Neighbourhood Submission of letter & map to Cornwall Council Cornwall Council approve designation. | November 2014 January 2015 |
|  | Stage 2: Ensuring community support for the neighbourhood planning process | Community Awareness Raising | August 2014 to March 2015 |
|  | Stage 3: Organisation | Set up Neighbourhood Planning Steering Group Develop and keep under review Project Plan Assess and keep under review the budget requirement Secure funding Identify sources of support | September 2014 |
| From capacity to action | Stage 4: Develop communication and engagement strategy | Understand nature of area, demographics, key stakeholders, accessibility needs etc. | January 2015 |
|  | Stage 5: Community engagement and scoping events | Initial scoping Key Stakeholder Identification and Engagement NP Community Engagement Activity A4D Community Engagement Activity | January to March 2015 March to May 2015 |
|  | Stage 6: Information gathering | Building the Evidence Base A4D researched | January to April 2015 January to April 2015 |
|  | Stage 7: Pulling community engagement results and evidence together, Working Groups engage community and stakeholders on site and policy options. | Define scope strategic vision and aims, outline content, thematic objectives and options; In-depth community and stakeholder involvement Prepare ‘Strategic Narrative’ A4D drafting process | April to June 2015 April to June 2015 |
| Producing the Draft Plan | Stage 8: Narrowing down the options and technical writing of draft plan. | A4D processed and approvals given (if necessary) Technical writing of NP ‘Sign off’ of NP by Town Council. | June 2015 June 2015 July 2015 |
| Refining and ‘Making’ the Plan | Stage 9: Testing and approving the Neighbourhood Plan | Pre-submission Consultation/ A4D Made and Notices Published Finalise Plan Submission of Plan for approval Examination | August 2015 October 2015 |
|  | Stage 10: Making of the Plan | Referendum Formal ‘Making’ as part of the planning policy framework. A4D Confirmed | March 2016 May 2016 June 2016 |
| Into action… | Stage 11: Delivering and monitoring the plan | Delivery of plan provisions…. | Thereafter…. |